## Home page
Test Case Name: Homepage for omsiddhidistributors
Sr No. | Title | Feature | Description | Steps to execute | Expected Result | Actual result | Status | Comments
1 | TC_HP_0001 | User Interface | Check all boxes and buttons | 1.Click to the website User should get the homepage | User should get homepage | User get the homepage | Pass
2 | TC_HP_0002 | User Interface | Check the category section | Check the category section | User should easily access the category section | Category section is easily accessible | Pass | It is having two number of bar for category section
3 | TC_HP_0003 | User Interface | Check the currency tab | 1. Click on the currency tab 2.select currency which is prefered | 1. It should get extended and show the different currencies | 1.It get extended and show different currencies | Pass
4 | TC_HP_0004 | User Interface | Check the currency flags by countries | Take a look at currency flags are given country wise | Currency flags should be country wise | Currency flags are country wise | Pass
5 | TC_HP_0005 | User Interface | Check title bar | 1. Go to the homepage 2.Take a look on title bar | 1.It should be aligned 2.It should contain main modules only | 1. It is aligned 2.It contains main modules only | Pass | I think the title bar will have to be more attractive and have to be in perfect format
6 | TC_HP_0006 | User interface | Check the search bar | 1.Check the search bar 2.Do try to search for something | It should be search the item which you have entered | It worked | Pass | 1.I think search bar will have to be in tittle bar 2.It have to be more easy to acess
7 | TC_HP_0007 | User Interface | Verify the registration tab | 1.Go to homepage 2.Click on the register tab | It should take the user at registration page | It takes the user at registration page | Pass
8 | TC_HP_0008 | User Interface | Verify the tab Wishlist | 1.Go to the homepage 2.Click on the Wishlist tab | It should take the user at wishlist's page | It takes the user at page of wishlist's | Pass
9 | TC_HP_0009 | User Interface | Verify the tab Shopping cart | 1.Go to the homepage 2.Click on the shopping cart tab | It should take user to the shopping cart page | It takes user to the shopping cart page | Pass
10 | TC_HP_0010 | User Interface | Verify the login tab | 1.Go to the homepage 2. Click on the login tab | It should take user to the login page | It takes user to the login page | Pass
11 | TC_HP_0011 | User Interface | Verify the logo | 1. Click on the logo | It should take user to the homepage | It takes user to the homeapge | Pass
12 | TC_HP_0012 | User Interface | Verify the add to cart logo | 1.Go to the product you want 2. Check the logo for add to cart | It should be easily visible and should be attractive | It is visible but not attractive and not having perfect visibility | Fail | I think the logo should be in colour
13 | TC_HP_0013 | User Interface | Verify the Manufacurer's box | 1. Go to the homepage 2.Check the manufacturer's box | It should be vary by category | 1.It is vary by category | Pass
14 | TC_HP_0014 | User Inteface | Verify the footer bar | 1.Go to the homepage 2.Check the all tabs on the footer bar | They all should easily accessible | They are not all easily accessible | Fail

## Register
Test case name: Registration page for Omsiddhidistributors
Sr No. | Title | Feature | Description | Steps to execute | Expected Result | Actual Result | Status
1 | TC_RG_00001 | User Interface | Check all the bottons and boxes | 1.Go to the website omsiddhidistributors.in 2. Click on the Registration page 3. Check all the buttons and boxes | 1. UI should be perfect 2. All the buttons and boxes should be aligned | 1. UI is perfect 2. All the buttons and boxes are aligned | Pass
2 | TC_RG_00002 | Required Fields | verify Registration page by entering all valid credentials | 1.Go to the registration page 2. Enter all valid credentials 3. Click on register tab | User should get successfully registered | User successfully registered | Pass
3 | TC_RG_00003 | Required Fields | Verify Registratiion page by entering all valid credentials but if you have already registered | 1. Go to the registration page 2. Enter all valid credentials 3. Click on register tab | User should get a message popup that you are already registered | User got a popup message that you are already registered | Pass
4 | TC_RG_00004 | Required Fields | Verify registration page by entering invalid email id and remaining all valid credentials | 1.Go to the registration page 2. Enter invalid email 3. Enter remaining credentials valid | User should get an popup message that wrong email | User got a popup message that wrong email | Pass
5 | TC_RG_00005 | Required Fields | Verify registration page by entering valid credentials but invalid password | 1. Enter the all valid credentials 2. Enter invalid password | User should have get an popup message about password rules | User get a popup message about password rules | Pass
6 | TC_RG_00006 | External authentication | Verify the external authentication process | 1.Enter all valid credentials 2. click on save | 1.User should redirected to the next page 2. User should get a warning message | User not redirected to the next page 2. User not get any warning message | Fail
7 | TC_RG_00007 | User Interface | Check the mandatory field logo appeared or not | 1. Go to the registration page 2. check the symbol for mandatory field appeared or not | Symbol should be appeared in red colour | Symbol appeared in red colour | Pass
8 | TC_RG_00008 | Required Field | Verify if any blank space appeared in any box | 1. Go the registration page 2. Enter credentials in all boxes except for one | User should get an popup message that mandatory field please fill | User got an popup message " that field required | Pass
9 | TC_RG_00009 | User Interface | Verify the country box for its extension | 1. Go to the registration page 2. Check the country box for its extension 3. Check the extension scrolling up and down or not | 1. User should get to know that there is extension by symbol 2. It should scrolling up and down for selection 3. It should got selected whichever the customer wants | 1. User know that there is a extension by upside arrow mark 2.It scrolling up and down for selection 3.it get selected whichever customer wants | Pass
10 | TC_RG_00010 | User Registration | Verify the registration tab | 1. Enter the all valid credentials 2. Click on the registration tab | User should get redirected to the next page | User got redirected to the next page | Pass
11 | TC_RG_00011 | OTP Verification | Verify the Registration by OTP verification message get on customers mobileno. Or not | 1. Enter the valid credentails 2.click on registeration tab | User should get redirected to the OTP verification page | User get redirected to the OTP verification page | Pass
12 | TC_RG_00012 | OTP Verification | Verify after entering OTP in required field | 1. Enter the OTP which will appeared on customers mobile number 2. Click on verify code | 1.The code should verified 2.User should get redirected to the next page 3. User should get popup message for successful registration | 1.The code verified 2.User got redirected to the next page User not get any popup message for successful registration | Pass
13 | TC_RG_00013 | OTP Verification | Verify after entering wrong OTP in required field | 1. Enter the wrong OTP in the box 2. Click on verify code | User should get a popup message that wrong OTP | User not get any popup message and it redirected to the same page again | Fail
14 | TC_RG_00014 | Required Field | Verify confirm password box | 1.Go to the registration page and enter valid credentials 2.Enter Password and confirm password field different | It should get a popup message that fields do not match | It got a popup message with fields do not match | Pass
15 | TC_RG_00015 | OTP Verification | Verify resend OTP tab | 1. Go to the OTP verification page 2. Click on the resend OTP tab | It should again send a OTP verification message on mobile number | It got a OTP verification message on mobile number | Pass

## Login
Test case name: Login page for omsiddhidistributors
Sr No. | Title | Feature | Description | Pre-requisites | Steps to execute | Expected Result | Actual Result | Status
1 | TC_LG_00001 | User Interface | Check all the boxes and buttons | Need to be a registerd user | 1. Go to the google website omsiddhidistributors.in 2. Click on the Login tab 3. Check page | 1.UI should be perfect 2. Text boxes and buttons should be aligned | 1.UI is perfect 2. Texr boxes and buttons are aligned | Pass
2 | TC_LG_00002 | User Interface | Check the signup option for new user | Need to be registerd user | 1.Click on the login tab 2. Check the signup button is working or not | By clicking on the signup button it should take user to the sign up page | By clicking on the sign up button it should take user to the sign up page | Pass
3 | TC_LG_00003 | User Interface | Verify login page | Need to be registerd user | 1. Go to the website 2. Click on the login page | It should successfully take customer to the next page | It take customer to the next page | Pass
4 | TC_LG_00004 | Required Fields | Enter a valid email and valid password | Need to be registerd user | 1. Enter a valid email and password 2. Click on the log in button | User should successfully login | User successfully logged in | Pass
5 | TC_LG_00005 | Required Fields | Enter an invalid email and password | Need to be registerd user | 1. Enter an invalid email 2. Enter a valid password 3.Click on the login | User should not log in and has to show error message | User not logged in and got an error message | Pass
6 | TC_LG_00006 | Required Fields | Enter a valid email and invalid password | Need to be registerd user | 1.Enter a valid email 2. Enter an invalid password 3. Click on the login | User should not log in and has to show an error message | User not logged in and got an an error message | Pass
7 | TC_LG_00007 | Forgot Password | Verify the tab " Forgot Password" | Need to be registerd user | 1.Go to the website 2. Click on the login tab 3. click on the forgot password tab | It should take to the user at password recovery page | It take user to password recovery page | Pass
8 | TC_LG_00008 | Reset Password | Verify the password recovery page | Need to be registerd user | 1.Click on to the forgot password tab 2.Enter a valid email | It should send an email to reset password | Got an email to reset password | Pass
9 | TC_LG_00009 | Reset password | Verify the password recovery page negatively | Need to be registerd user | 1. Click on the forgot password tab 2.Enter an invalid email | User should not log in and has to show error message | User not logged in and got an error message | Pass
10 | TC_LG_00010 | Required Field | Enter blank space at password box | Need to be registerd user | 1. Enter a valid email 2.Keep blank password box 3. Click on log in | User should not log in and show an error message | User not logged in and got an error message | Pass
11 | TC_LG_00011 | Required Field | Enter blank space at email box | Need to be registerd user | 1. Keep blank email box 2. Enter a valid password | User should not log in and show an error message | User not logged in and got an error message | Pass
12 | TC_LG_00012 | User login | Verify remember me tab | Need to be registerd user | 1.Enter valid email and password 2. Tick on the remember me tab | It should save password for later | It saved password for later | Pass
13 | TC_LG_00013 | User login | Verify remember me tab | Need to be registerd user | 1. Enter valid email and password 2. Do not tick on remember me tab | It should not save password for later | It saved password for later | Pass

## Wishlist
Testcase Name: Wishlist page for omsiddhidistributors
Sr No. | Title | Feature | Description | Steps to execute | Expected result | Actual Result | Status | Comments
1 | TC_WL_001 | User Interface | Verify Wishlist tab | 1. Go to home page 2.Click on the tab wishlist | It should take user to the wishlist's page | It takes user to the wishlist's page | Pass
2 | TC_WL_002 | User Interface | Verify inner function of wishlist tab | 1. go to home page 2. Click on the wishlist tab 3.Check all the item which you wishlisted are added to the page or not | 1.All wishlisted items should be available in the page 2. They should be easily accessible 3. They should have contain all basic information about the product | 1.All wishlisted items are available in that page 2. They are easily accessible 3.They contain all basic information in row format | Pass
3 | TC_WL_003 | User Inteface | Verify the tab add to cart which is in wishlist page | 1.Go to the wishlist page 2.Tick on the product which you want to add in to the cart 3. Click on the add to cart option | 1.It should add the product in your cart 2.It should get a popup message that your item is added in to the cart | 1.It add the product into the cart 2. It do not get any popup message | Pass | I think the popup message is important
4 | TC_WL_004 | User Interface | Verify the symbol of wishlist appeared on home page | 1. Go to the homepage 2. Go to any product 3. Check the symbol of wishlist | It should be easily visible | It easily visible but need to be more perfect | Pass
5 | TC_WL_005 | User Interface | Verify the remove option which is in the wishlist page | 1. Go to the wishlist tab 2. Click on the remove symbol | The product should get removed from the wishlist | The product get temoved from wishlist | Pass
6 | TC_WL_006 | User Interface | Verify the remove option logo | 1. Go to the wishlist tab 2.Take a look at the remove symbol | It should be in colour and easily visible | It is in colour and easily visible | Pass
7 | TC_WL_007 | User Interface | Verify the Update wishlist tab | 1. Go to the Wishlist tab 2. Click on the update wishlist tab | It should get update the wishlist | It get updated wishlist | Pass | Is it necessary to give an option?
8 | TC_WL_008 | User Interface | Verify the tab email a friend | 1. Go to the wishlist tab 2.Click on the email a friend tab | It should go to the next page for email a friend | It go to the next page | Pass
9 | TC_WL_009 | User Interface | Verify the page email your wishlist to your friend | 1. Go to the wishlist tab 2. Click on the email a friend tab 3.Check the page "email your wishlist to a friend | 1.It should be perfectly alligned 2.The boxes and buttons should be perfect 3.Visually it has to be perfect | 1.It is perfectly aligned 2. The boxes and buttons are perfect 3. Visually it is perfect | Pass
10 | TC_WL_010 | Email a friend | Verify the email a friend page | 1.Go to the email a friend page 2.Enter a friend's email 3.Enter your email 4. write a message 5.Click on the send email | 1.It should not accept invalid email 2. It should accessed by only a registered user 3. Message should be fully optional | 1.It do not accept invalid email 2.It is accessed by registered user otherwise it shows a error message that you have to be registered 3. Message is optional | Pass
11 | TC_WL_011 | User Interface | Verify the send email tab | 1.Enter the all valid credentials in that fields 2. Click on the send tab | It should send an email to friend and popup a message that email sent successfully | It send an email to the friend and popup a message that email sent successfully | Pass
12 | TC_WL_012 | User Interface | Verify the tab Quantity | 1. Go to the wishlist page 2. Click on the quantity tab | 1. It should have space to enter the required quantity of the product | 1. It have space to enter the required quantity of the product | Pass
13 | TC_WL_013 | User Interface | Verify the product details | 1. Go to the wishlist 2.Click on the product details | It should open the detailed information about the product | It opens the detailed information of the product | Pass
14 | TC_WL_014 | User Interface | Verify the logo of the product | 1. Go to the wishlist page 2. Check the logo of the product | 1. It should be display with name 2. It should having standard size | 1. It display with name 2. It having standard size | Pass
15 | TC_WL_015 | User Interface | Verify the add to cart process | 1.Go to the wishlist page 2.Check for the option for selecting the product to add into the cart 3. Click on the add to cart option | 1. It should have the option for selection of the product to add into the cart 2.It should add only selected item into the cart | 1.It have the option for the selection of the product to add into the cart 2.It add only selected item into the cart | Pass
16 | TC_WL_016 | User Interface | Verify the functionality of the wishlist tab | 1. Go to the wishlist tab 2.Check all internal functionality one by one | 1.It should have all related information 2. It should easy to access | 1.It is having all related information 2. It is easily accessible | Pass

## Shopping cart
Testcase Name: Shopping cart page for omsiddhidistributors
Sr No. | Title | Feature | Description | Steps to execute | Expected result | Actual Result | Status | Comments
1 | TC_SH_001 | User Interface | Verify the shopping cart tab | 1. Go to the homepage 2. Click on the shopping cart tab | 1.It should take user to the shopping cart page 2. It should be easily accessible | 1.It Take user to the shopping cart page 2.It is easily accessible | Pass
2 | TC_SH_002 | User Interface | Verify the list format of the shopping cart page | 1. Go to the shopping cart page 2. Overlook the format of the shoppong cart page | 1.It should be in list or grid format 2.It should be having all related information | 1.It is in list format 2. It having all related information | pass
3 | TC_SH_003 | User Interface | Verify the update shopping cart tab | 1. Go to the shopping cart page 2. Click on the update shopping cart tab | It should update the shopping cart | It updates shopping cart | Pass
4 | TC_SH_004 | User Interface | Verify the continue shopping tab | 1. Go to the shopping cart page 2.Click on the continue shopping tab | It should go to the homepage | It goes to the search page | Fail
5 | TC_SH_005 | User Interface | Verify the Estimate shopping tab | 1. Go to the shopping cart page 2.Click on the estimate shopping tab | It should take the user to the next page | It takes the user to the next page | Pass
6 | TC_SH_006 | User inteface | Verify the shop to page | 1. Go to the shopping cart page 2. Click on the estimate shopping page 3. Overlook all the buttons, boxes and allignments | 1.It should be perfectly visible 2. The buttons, boxes and allignmets should be perfect | 1. It is pefectly visible 2. The buttons, boxes and allignments are perfect | Pass
7 | TC_SH_007 | Required fields | Verify the Ship to page's country box | 1.Go to the Estimated shopping tab 2. Click on the country box | 1. It should give a list of countries after click on the box 2.It should have sign notation to recognise list to extend 3.It should get extended after clicking on the sign notation | 1.It give a list of countries after click on the box 2. It have sign notation downside arrow to recognise list to extend 3. I tget extended after clicking on the sign notation 4. It showing it a mandatory field with notation star in red colour | Pass
8 | TC_SH-008 | Required fields | Verify the other option | 1. Go to the estimated shopping tab 2. Click on the other box | 1.It should give other options in list format 2. It should be give by any notation | 1.It just giving other option for other box 2. It gived by notation downside arrow | Pass
9 | TC_SH_009 | Required fields | Verify the Zip/ postal code | 1.Go to the Estimated shopping tab 2. Click on the Zip/postal code | 1.It should have the access to enter the zip code in the box 2. It should be mandatory 3. It should give message error if it not entered | 1.It have the access to enter the zip code in the box 2. It is showing mandatory field with notation star 3. It is showing message error if it is not entered | Pass
10 | TC_SH_010 | Required fields | Verify the Shipping method | 1. Go to the estimated shopping tab 2. Enter zip code 3.Verify the shipping method | 1. It should go to the shipping method page after entering zip code 2. It should give other options for delivery after entering zip code | 1.It goes to the shipping method page after entering zip code 2. It gives other options for delivery after entering zip code | Pass
11 | TC_SH_011 | User Interface | Verify the apply button | 1.Go to the estimated shopping tab 2. Enter zip code 3. Click on the required option 4. Click on the apply button | It should submit your requirement with a message | 1. It submits requirement but it directly goes to the estimated shopping page 2. When we again open the tab it gives an error message that option not available | Fail
12

## User Interface
Testcase Name: Login/Logout for omsiddhidistributors
Sr No. | Title | Description | Steps to execute | Expected Result | Actual Result | Status
1 | TC_LO_001 | Verify the logout tab | 1.Go to the website omsiddhidistributors.in 2. Click on the logout tab | It should get logout after clicking on the tab | It get logout after clicking on the tab | Pass
2 | TC_LO_002 | Verify the login tab | 1.Go to the website omsiddhidistributors.in 2. Click on the login tab | It should take the user to the login page | It takes the user to the login page | Pass
3 | TC_LO_003 | Verify the logo | 1. Go to the website omsiddhidistributors.in 2 .Click on the logo | It should take user to the home page | It takes user to the home page | Pass

## Title Bar
Testcase Name: Title bar and Side bar for omsiddhidistributors.in
Sr No. | Title | Description | Steps to execute | Expected Result | Actual Result | Status
1 | TC_TB_001 | Verify the title bar | 1. Go to the website omsiddhidistributors.in 2. Check the Titlebar | It should be aligned with some useful information | It is aligned with useful information | Pass
2 | TC_TB_002 | Verify the Information given on title bar | 1. Go to the website omsiddhidistributors.in 2. Go to the category wise option 3. Check the information provided by it correct or not | It should be having classififcation category wise | It is having classififcation categorywise | Pass
3 | TC_TB_003 | Check if it is giving right information or not | 1. Go to the website omsidddhidistributors.in 2. Check all the information in evey category if it is right or wrong | It should be having perfect information in every classification of category | It is not having perfect classification of vegetable category | Fail
4 | TC_SB_001 | Verify the side bar | 1. Go to the website omsiddhidistributors.in 2. Check the side bar | It should having categorywise all information about the product | It is having categorywise all information about the product | Pass
5 | TC_SB_002 | Verify the side bar | 1. Go to the website omsiddhidistributors.in 2. Check the allignment and logo | It should be pefectly alligned | It is perfectly aligned | Pass
6 | TC_SB_003 | Verify next page tab | 1. Go to the website omsiddhidistributors.in 2. Click on the number of page or click on the next page tab | It should be going to the next page | It is going to the next page | Pass

## Bottom Bar
Testcase Name: Bottom bar for omsiddhidistributors.in
Sr No. | Title | Description | Steps to execute | Expected Result | Actual Result | Status
1 | TC_BB_001 | Verify the bottom bar | 1. Go to the website omsiddhidistributors.in 2. Check the allignement user interface of the bottom bar | It should be perfectly aligned and visible to the user | It is perfectly aligned and visible to the user | Pass
2 | TC_BB_002 | Verify the bottom bar options | 1. Go to the website omsiddhidistributors.in 2. Go to the bottom bar 3. Check all the options for bottom bar | It should be open on one click and should be giving all the information | It is open on one click and giving all the related information | Pass

## Failed Test cases
Failed Test cases for omsiddhidistributors
Sr No. | Title | Feature | Description | Pre-requisites | Steps to execute | Expected Result | Actual Result | Status
1 | TC_HP_0012 | User Interface | Verify the add to cart logo | Home Page | 1.Go to the product you want 2. Check the logo for add to cart | It should be easily visible and should be attractive | It is visible but not attractive and not having perfect visibility | Fail
2 | TC_HP_0014 | User Inteface | Verify the footer bar | Home Page | 1.Go to the homepage 2.Check the all tabs on the footer bar | They all should easily accessible | They are not all easily accessible | Fail
3 | TC_RG_00006 | External authentication | Verify the external authentication process | Registration Page | 1.Enter all valid credentials 2. click on save | 1.User should redirected to the next page 2. User should get a warning message | User not redirected to the next page 2. User not get any warning message | Fail
4 | TC_RG_00012 | OTP Verification | Verify after entering OTP in required field | Registration Page | 1. Enter the OTP which will appeared on customers mobile number 2. Click on verify code | 1.The code should verified 2.User should get redirected to the next page 3. User should get popup message for successful registration | 1.The code verified 2.User got redirected to the next page User not get any popup message for successful registration | Pass
5 | TC_RG_00013 | OTP Verification | Verify after entering wrong OTP in required field | Registration Page | 1. Enter the wrong OTP in the box 2. Click on verify code | User should get a popup message that wrong OTP | User not get any popup message and it redirected to the same page again | Fail
6 | TC_SH_004 | User Interface | Verify the continue shopping tab | Shopping cart | 1. Go to the shopping cart page 2.Click on the continue shopping tab | It should go to the homepage | It goes to the search page | Fail
7 | TC_SH_011 | User Interface | Verify the apply button | Shopping cart | 1.Go to the estimated shopping tab 2. Enter zip code 3. Click on the required option 4. Click on the apply button | It should submit your requirement with a message | 1. It submits requirement but it directly goes to the estimated shopping page 2. When we again open the tab it gives an error message that option not available | Fail
8 | TC_TB_003 |  | Check if it is giving right information or not |  | 1. Go to the website omsidddhidistributors.in 2. Check all the information in evey category if it is right or wrong | It should be having perfect information in every classification of category | It is not having perfect classification of vegetable category | Fail